## Sheet1
Research Park Foundation
SARATHI Entrepreneurship Development (Incubation) Programme
Daily Activity Dairy
Name of Participant : Rushikesh Jagdevrao Bhumkar
Title of the Project : Delicious Dabbas
Date | Name of the Days | Work / Activity Description
2024-09-01 | Sunday | Begin integrating the meal customization feature with the backend. Create and upload a banner on Instagram showcasing the customization process.
2024-09-02 | Monday | Conduct internal testing on the meal customization feature. Review and improve the UI for the customization interface based on feedback.
2024-09-03 | Tuesday | Start developing the feedback feature for the meal customization. Upload a LinkedIn post introducing the customization feature to users.
2024-09-04 | Wednesday | Work on integrating the feedback system with the database. Design wireframes for the user profile page.
2024-09-05 | Thursday | Continue developing the user profile page and integrate with backend user data. Share a Facebook post updating users on the customization feature’s progress.
2024-09-06 | Friday | Begin designing the order tracking feature interface in Figma. Test and debug the profile page functionalities.
2024-09-07 | Saturday | Start development of the order tracking feature. Upload an Instagram post showing design progress of the user profile page.
2024-09-08 | Sunday | Continue developing and testing the order tracking feature. Refine meal customization logic based on user testing feedback.
2024-09-09 | Monday | Review and finalize the UI/UX for the order tracking feature. Share a LinkedIn post announcing progress on user profile and order tracking features.
2024-09-10 | Tuesday | Conduct a full review of all app features for consistency and user flow improvements. Work on improving the app’s performance by optimizing the backend logic.
2024-09-11 | Wednesday | Begin designing the order history analytics dashboard in Figma. Share a Facebook post about recent UI improvements and upcoming features.
2024-09-12 | Thursday | Start development on the order history analytics dashboard. Continue testing user feedback feature, ensuring it's working smoothly with the backend.
2024-09-13 | Friday | Refine UI/UX for the order history screen based on feedback.
2024-09-14 | Saturday | Begin initial work on integrating user notifications for meal status updates. Share a Facebook update on the status of analytics dashboard development.
2024-09-15 | Sunday | Continue work on meal status notifications, focusing on backend logic. Test the meal customization and user profile features.
2024-09-16 | Monday | Review and refine meal notifications feature, ensuring timely and accurate updates. Upload an Instagram post highlighting the development of notification features.
2024-09-17 | Tuesday | Conduct internal testing on all integrated features (customization, tracking, notifications). Share a LinkedIn post summarizing the app’s current development status.
2024-09-18 | Wednesday | Design the onboarding process for new users, focusing on a simple and clean UI. Continue optimizing the performance of the meal ordering and customization processes.
2024-09-19 | Thursday | Start development of the onboarding process, integrating it with user registration. Share a Facebook post about the app’s new onboarding process and its ease of use.
2024-09-20 | Friday | Finalize and test the onboarding process, ensuring smooth navigation and functionality. Work on refining the UI/UX for the onboarding process based on initial feedback.
2024-09-21 | Saturday | Begin work on adding additional meal customization options based on feedback. Share an Instagram post highlighting the ease of the onboarding process.
2024-09-22 | Sunday | Continue developing the additional customization options, ensuring flexibility for users. Test the newly developed onboarding and customization options.
2024-09-23 | Monday | Begin development of meal recommendations based on user preferences and history. Share a LinkedIn post discussing the new customization options and meal recommendations.
2024-09-24 | Tuesday | Review the overall app performance, focusing on load times and responsiveness. Refine the meal recommendation algorithm to provide more accurate results.
2024-09-25 | Wednesday | Continue improving the app’s UI consistency, ensuring brand alignment. Share a Facebook post highlighting the app’s meal recommendation feature.
2024-09-26 | Thursday | Focusing on load times and responsiveness. Optimized the meal recommendation algorithm to provide more accurate results based on recent user feedback.
2024-09-27 | Friday | Continued testing the meal recommendation algorithm. Worked on improving the UI consistency, ensuring all elements align with the app’s brand design.
2024-09-28 | Saturday | Customization, tracking, and notifications. Uploaded an Instagram post showcasing the user-friendly meal customization interface.
2024-09-29 | Sunday | Continued reviewing the overall app performance, with a focus on reducing load times. Improved the accuracy of meal recommendations by refining the recommendation algorithm further.
2024-09-30 | Monday | Conducted internal testing on meal recommendations to ensure users get personalized results. Worked on refining the backend logic for quicker response times during peak usage.
2024-10-01 | Tuesday | Integrated additional user feedback into the meal recommendation system to enhance customization options. Uploaded a LinkedIn post updating users about the improvements in app performance.
2024-10-02 | Wednesday | Continued working on optimizing app load times and responsiveness. Began designing a new user feedback form to gather input on recent app updates.
2024-10-03 | Thursday | Review the overall app performance, focusing on load times and responsiveness. Refine the meal recommendation algorithm to provide more accurate results.
2024-10-04 | Friday | Begin integrating the meal customization feature with the backend. Create and upload a banner on Instagram showcasing the customization process.
2024-10-05 | Saturday | Work on integrating the feedback system with the database. Design wireframes for the user profile page.
2024-10-06 | Sunday | Performed a final review of the app’s overall performance after all optimizations. Uploaded an Instagram post showcasing new features, including enhanced meal recommendations.